## Project timeline plan
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 43040 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Problem statement, initial project plan | 2017-11-01 | 2017-11-08 | 7
Project proposal | 2017-11-09 | 2017-11-18 | 9
Literature review, algorithm knowledge preparation | 2017-11-18 | 2017-11-22 | 4
Azure platform setup, data preparation, data clean | 2017-11-23 | 2017-11-30 | 7
Datasets merge and further clean | 2017-12-01 | 2017-12-06 | 5
Pipeline presentation | 2017-12-03 | 2017-12-06 | 3
Data imputation optimization using GLRM | 2018-01-03 | 2018-01-10 | 7
K-means implementation -- focus on number of K | 2018-01-11 | 2018-01-25 | 14
K-means implementation -- focus on initial convergence | 2018-01-25 | 2018-02-08 | 14
K-means implementation -- focus on extention of definition of mean | 2018-01-25 | 2018-02-08 | 14
K-means implementation -- focus on algorithm robustness | 2018-01-25 | 2018-02-08 | 14
K-means algorithm performance test on MG-Hedge | 2018-02-08 | 2018-02-15 | 7
GMM implementation | 2018-02-15 | 2018-03-01 | 14
Hierachical implementation | 2018-02-15 | 2018-03-01 | 14
K-means optimization | 2018-02-15 | 2018-03-01 | 14
Project results wrap up and code polish | 2018-03-02 | 2018-03-08 | 6
Report and presentation | 2018-03-09 | 2018-03-15 | 6
Project end | 2018-03-16 | 2018-03-17 | 1
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Project with % complete
Task Name | Stakeholders | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43040 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Problem statement, initial project plan | All | 2017-11-01 | 2017-11-08 | 7 | 7 | 0 | 100%
Project proposal | All | 2017-11-09 | 2017-11-18 | 9 | 6.3 | 2.7 | 70%
Literature review, algorithm knowledge preparation | All | 2017-11-18 | 2017-11-22 | 4 | 0 | 4 | 0%
Azure platform setup, data preparation, data clean | All | 2017-11-23 | 2017-11-30 | 7 | 0 | 7 | 0%
Datasets merge and further clean | All | 2017-12-01 | 2017-12-06 | 5 | 0 | 5 | 0%
Pipeline presentation | All | 2017-12-03 | 2017-12-06 | 3 | 0 | 3 | 0%
Data imputation optimization using GLRM | All | 2017-01-03 | 2017-01-18 | 15 | 0 | 15 | 0%
K-means implementation -- focus on number of K | All | 2017-01-11 | 2017-01-25 | 14 | 0 | 14 | 0%
K-means implementation -- focus on initial convergence | One team member | 2017-01-25 | 2017-02-08 | 14 | 0 | 14 | 0%
K-means implementation -- focus on extention of definition of mean | One team member | 2017-01-25 | 2017-02-08 | 14 | 0 | 14 | 0%
K-means implementation -- focus on algorithm robustness | One team member | 2017-01-25 | 2017-02-08 | 14 | 0 | 14 | 0%
K-means algorithm performance test on MG-Hedge | All | 2017-02-08 | 2017-02-15 | 7 | 0 | 7 | 0%
GMM implementation | One team member | 2017-02-15 | 2017-03-01 | 14 | 0 | 14 | 0%
Hierachical implementation | One team member | 2017-02-15 | 2017-03-01 | 14 | 0 | 14 | 0%
K-means optimization | One team member | 2017-02-15 | 2017-03-01 | 14 | 0 | 14 | 0%
Project results wrap up and code polish | All | 2017-03-02 | 2017-03-08 | 6 | 0 | 6 | 0%
Report and presentation | All | 2017-03-09 | 2017-03-15 | 6 | 0 | 6 | 0%
Project end | All | 2017-03-16 | 2017-03-17 | 1 | 0 | 1 | 0%
[8 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[9 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.